## Sheet1
	Start Date	End Date	Task description	Task type	Status
Week 1&2	21-Oct-2019	4-Nov-2019	Build an android app	Mandatory	Abandoned
	5-Oct-2019	6-Nov-2019	Working with RecyclerView	Optional	DONE
	7-Nov-2019	8-Nov-2019	Connecting to the internet	Optional	DONE
Week 3	18-Nov-2019	24-Nov-2019	Building the navigation bar	Mandatory	DONE
Week 4	25-Nov-2019	27-Nov-2019	Learn how to use Firebase	Optional	Abandoned
	28-Nov-2019	30-Nov-2019	Building a flexbox container	Optional	DONE
Week 5	9-Dec-2019	12-Dec-2019	Create the input form	Mandatory	DONE
	13-Dec-2019	15-Dec-2019	Create the a page for the archive	Mandatory	DONE
Week 6	16-Dec-2019	22-Dec-2019	Change the layout of the notes	Mandatory	DONE
Week 7	23-Dec-2019	29-Dec-2019	Add notes with JavaScript	Mandatory	DONE
Week 8	3-Jan-2020	5-Jan-2020	Create the context menu	Mandatory	DONE
Week 9	6-Jan-2020	8-Jan-2020	Technical docuemntation	Mandatory	DONE
	9-Jan-2020	10-Jan-2020	Presentation	Mandatory	DONE
	11-Jan-2020	12-Jan-2020	Finishing up&user guide	Mandatory	DONE

Deadline	13-Jan-2020